## Overview
TEC Form Test Plan
Purpose | Verify that users can access the TEC assessment form, complete and save assessments, submit valid assessments, and that administrators can manage users, departments, and roles.
Test setup | Application running locally or on the Linux server; PostgreSQL available; current Chrome, Edge, or Firefox; test email address; test admin data.
Local startup | npm install, then npm run dev
Deployed path | Test the configured URL, including /tec when applicable.
Acceptance summary | Login gate works, required fields block incomplete actions, drafts save and reload, valid submissions reach the thank-you page, admin CRUD works, and deployment smoke checks pass.

## Test Cases
ID | Test | Steps | Expected result
T01 | Login gate | Open the application root in a new browser session or clear tecFormLoggedIn from local storage. | User is redirected to the login page.
T02 | Login without credentials | On the login page, click Login without entering credentials. | User is taken to the TEC assessment form. No username or password is requested.
T03 | Return to login when logged out | Clear tecFormLoggedIn, then open the form URL again. | User is redirected to login and cannot view the form until clicking Login.
T04 | Form navigation | Log in and move forward and backward through the form steps. | The correct step is displayed and navigation does not crash or lose entered values.
T05 | Reviewing Department required | On the Reviewing Department step, leave the department blank and attempt to continue or submit. | Submission or continuation is blocked and a clear required-field message is shown.
T06 | Email required | Leave the email blank and attempt to continue, save, or submit. | The action is blocked and the user is told to complete the Email field.
T07 | Valid department selection | Select each available reviewing department where practical. | The selected department is retained and the appropriate department assessment step opens.
T08 | Save draft | Enter an email and some form data, then use the save action. | A success message is shown and the draft is stored in the database.
T09 | Load saved draft | Reopen the form using the same email after saving a draft. | Previously saved form data is loaded.
T10 | Submit valid form | Complete all required fields and follow the form flow to submission. | The submission succeeds, the success state is shown, and the user is redirected to the thank-you page.
T11 | Export form | Enter an email and form data, then use the PDF or export action. | A printable export opens and contains the saved form values.
T12 | Admin navigation | Log in and open Admin from the sidebar. | The admin page opens with Users, Departments, and Roles tabs.
T13 | User management | Add, edit, search, and delete a test user. | Each operation succeeds and the displayed list reflects the change.
T14 | Department management | Add, edit, and delete a department that is not in use. | Each operation succeeds and the displayed department list updates.
T15 | Department delete protection | Attempt to delete a department referenced by existing data. | The delete is blocked with an explanatory message.
T16 | Role management | Add, edit, and delete a test role. | Each operation succeeds and the displayed role list updates.
T17 | API/database failure handling | Temporarily stop the database or use an invalid database configuration, then load or save data. | The application shows a useful error state and does not silently report success.

## Acceptance Criteria
ID | Acceptance criterion | Status
A01 | A user cannot access the form before clicking Login. | Not Run
A02 | Login works without credentials. | Not Run
A03 | Required-field validation prevents incomplete continuation and submission. | Not Run
A04 | Drafts save and reload correctly. | Not Run
A05 | Valid submissions reach the thank-you page and persist in the database. | Not Run
A06 | Admin CRUD operations work for users, departments, and roles. | Not Run
A07 | The deployed application works through the configured Nginx path. | Not Run
A08 | No blocking browser console, server, or database errors remain after the smoke test. | Not Run

## Execution Log
Test run date | Environment | Tester | Result | Notes